## Sprint1
ID | Name | Description / Metodology | Expected duration (h) | Completed
38.5
ID0001 | Get information | We need to have enough knowledge about the methods we will use | 16 | 50%
ID0001_T1 | Read the papers | Reading and interpretation of the documentation and methods provided for the project. | 12 | 100%
ID0002_T2 | Find extra documentation | Search for additional resources if necessary to achieve the required knowledge | 4 | 0
ID0002 | Deliverable 1 | Prepare and send Deliverable 1 before 05/04/2019 | 4 | 0
ID0002_T1 | Summary | Carry out a brief summary analyzing the different techniques of feature selecction, including L2-AROM and PS-L2-AROM | 2 | 0
ID0002_T2 | Planiffication | Prepare the planning of the project, describing the tasks with their description, metodology and expected task duration | 2 | 0
ID0003 | Implement of PS-L2-AROM | Implement method PS-L2_AROM | 9.5
ID0003_T1 | Studied L2-AROM | Studied provided implemented method of L2-AROM. Check its correct operation with some unit test and sample data | 1.5 | 0
ID0003_T2 | Implement approach of PS-L2-AROM | From method L2-AROM implement new variable ranking approach based on the PS-L2-AROM | 6 | 0
ID0003_T3 | Test PS-L2-AROM | Carry out some unit test on the PS-L2-AROM implemented in the previous task. Check its correct operation through executions with some example data | 2 | 0
ID0004 | Reproduce experiments | Adjust the developed approach of PS-L2-AROM method to reproduce the experiments perfomed in paper [4] using the provided datasets | 4 | 0
ID0005 | Final analysis | Present the final results obtained and analyze the feature selection stability | 5 | 0
ID0005_T1 | Analysis the results | Analyse the results obtanined and the feature selecction stability | 2 | 0
ID0005_T2 | Write the report | Write a report with the result obtained and its analysis. Also incluse the code of the project, clean and commented | 3 | 0